## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (AI-Powered Customer Support Quality Auditor) | MUST HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S1 | S1 | US-001 | Milestones Discussed | MUST HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S1 | S1 | US-001 | SRS Planned | SHOULD HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S1 | S1 | US-001 | Tech Stack Finalized | MUST HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S1 | S1 | US-001 | GIT initialization and repository setup | MUST HAVE | GIT | Aditya Kumar Sahu | 3- Completed
S2 | S2 | US-001 | Project Initialization and Concepts | MUST HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S2 | S2 | US-001 | Brainstroming | COULD HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S2 | S2 | US-001 | Libraries and Workflow | MUST HAVE | WebRTC,Python | Aditya Kumar Sahu | 3- Completed
S2 | S2 | US-001 | Basic Whisper Setup | MUST HAVE | Whisper STT | Aditya Kumar Sahu | 3- Completed
S3 | S3 | US-001 | Concepts of Different types Embedding | SHOULD HAVE | WORD2VEC | Aditya Kumar Sahu | 3- Completed
S3 | S3 | US-001 | Tranformers | SHOULD HAVE | OpenAI | Aditya Kumar Sahu | 3- Completed
S3 | S3 | US-001 | Natural Language Processing | SHOULD HAVE | Gemini AI Studio | Aditya Kumar Sahu | 3- Completed
S3 | S3 | US-001 | AI API's | SHOULD HAVE | Gemini AI Studio | Aditya Kumar Sahu | 3- Completed
S3 | S3 | US-001 | RAG Concepts | SHOULD HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S3 | S3 | US-001 | RAG Inplementation Overview | SHOULD HAVE | LangChain | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Make Application Orchestrator | MUST HAVE | python,Streamlit | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Audio Processor | MUST HAVE | Senko/WebRTC | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Chat Normalizer | MUST HAVE | Python,JSON | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | DB Manager and RAG engine | MUST HAVE | Sqlite/Langchain | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Auditor | MUST HAVE | Google Gen AI | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Reporting | MUST HAVE | SMTPLIB & FPDF | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Bugs Error fixing code upts policy update personal reporting code | MUST HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Handling env variables and policy fiies | MUST HAVE | DOT-ENV | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | Theory and Implementation of Docker | SHOULD HAVE | No Dependency | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | DOCKER CONFIGURATION | SHOULD HAVE | Docker | Aditya Kumar Sahu | 3- Completed
S4 | S4 | US-001 | DOCKER IMAGE AND CONTAINER | SHOULD HAVE | Docker | Aditya Kumar Sahu | 3- Completed
S5 | S5 | US-001 | Documentation and Implementation | SHOULD HAVE | GITHUB | Aditya Kumar Sahu | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 58 | 10.5 | 14.5 | 11 | 8.5 | 4 | 4 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
S1 | 1 | Introduction to project (AI-Powered Customer Support Quality Auditor) | 7th Dec | 7th Dec | Aditya Kumar Sahu | Others | 3- Completed | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 | 2 | Milestones Discussed | 7th Dec | 13th Dec | Aditya Kumar Sahu | Others | 3- Completed | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 | 3 | SRS Planned | 7th Dec | 13th Dec | Aditya Kumar Sahu | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 | 4 | Tech Stack Finalized | 7th Dec | 13th Dec | Aditya Kumar Sahu | Others | 3- Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S1 | 5 | GIT initialization and repository setup | 7th Dec | 13th Dec | Aditya Kumar Sahu | Others | 3- Completed | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2 | 6 | Project Initialization and Concepts | 15th Dec | 19th Dec | Aditya Kumar Sahu | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2 | 7 | Brainstroming | 15th Dec | 19th Dec | Aditya Kumar Sahu | Others | 3- Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2 | 8 | Libraries and Workflow | 15th Dec | 19th Dec | Aditya Kumar Sahu | Coding | 3- Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2 | 9 | Basic Whisper Setup | 15th Dec | 19th Dec | Aditya Kumar Sahu | Coding | 3- Completed | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 10 | Concepts of Different types Embedding | 2025-12-22 | 2026-01-02 | Aditya Kumar Sahu | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 11 | Tranformers | 2025-12-22 | 2026-01-02 | Aditya Kumar Sahu | Others | 3- Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 12 | Natural Language Processing | 2025-12-22 | 2026-01-02 | Aditya Kumar Sahu | Others | 3- Completed | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 13 | AI API's | 2025-12-22 | 2026-01-02 | Aditya Kumar Sahu | Coding | 3- Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 14 | RAG Concepts | 2025-12-22 | 2026-01-02 | Aditya Kumar Sahu | Others | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 15 | RAG Inplementation Overview | 2025-12-22 | 2026-01-02 | Aditya Kumar Sahu | Others | 3- Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 16 | Make Application Orchestrator | 2026-01-05 | 10th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 17 | Audio Processor | 2026-01-05 | 10th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 18 | Chat Normalizer | 2026-01-05 | 10th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 19 | DB Manager and RAG engine | 2026-01-05 | 10th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 20 | Auditor | 2026-01-05 | 10th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 21 | Reporting | 2026-01-05 | 10th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 22 | Bugs Error fixing code upts policy update personal reporting code | 2026-01-05 | 17th Jan | Aditya Kumar Sahu | System Test | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 23 | Handling env variables and policy fiies | 2026-01-05 | 17th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 24 | Theory and Implementation of Docker | 2026-01-05 | 24th Jan | Aditya Kumar Sahu | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 25 | DOCKER CONFIGURATION | 2026-01-05 | 24th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 26 | DOCKER IMAGE AND CONTAINER | 2026-01-05 | 24th Jan | Aditya Kumar Sahu | Coding | 3- Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S5 | 27 | Documentation and Implementation | 2026-01-25 | 31st Jan | Aditya Kumar Sahu | Others | 2- In Progress | 3 | bar: Day 1 to Day 3
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 9 | Performance of the Diarizer | Found alternatives like Senko
Sprint 2 | Day 10 | Wheel issue | Download C++ Visual Studio and rollback python
Sprint 4 | Day 36 | Wheel system Dependency | Moved to Docker
Sprint 4 | Day 37 | Policy inefficent | Collected Data and made a proper file

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 2015-12-01 | 2019-12-01 | ALL | Maintaining code modularity | Writing unstructured codes | Diarization and Further setup | Use principles of HLD & LLD
2 | Sprint 4 | 2029-12-01 | 2026-01-23 | ALL | Env variables and dependcies standards | using alternative packages | Setup Like Docker | Used Docker to resolve the issue
3
4
5
6
7